## Action Plan
ACTION PLAN FOR ENGLISH LEARNING SKILL HANDBOOK - SSC - GROUP 3
Study week | Week Day | Date | Activity | Assignee | Recommendations | Criteria/KPI | Expected results
1 | Mon | 2019-09-09
| Tue | 2019-09-10
| Wed | 2019-09-11 | Build team | PhongVH |  | 4-5 members | Team is built with 5 members
| Thu | 2019-09-12
| Fri | 2019-09-13 | Decide on project subject | MienNTH
| Sat | 2019-09-14
| Sun | 2019-09-15
2 | Mon | 2019-09-16 | Do research on handbook market | TrungDQ AnhPT |  | Have a report for team before 18/9
| Tue | 2019-09-17
| Wed | 2019-09-18 | Create initial report | All |  |  | Finish content on 20/9
| Thu | 2019-09-19
| Fri | 2019-09-20 | Create action plan | MienNTH |  |  | Finish on 20/9
| Sat | 2019-09-21 | Format Report
| Sun | 2019-09-22
3 | Mon | 2019-09-23 | Learn how to write proposal | All | Teacher clarifies any confusion |  | Have basic knowledge of a proposal and know what is included in a proposal
| Tue | 2019-09-24
| Wed | 2019-09-25 | Write proposal | All |  |  | Finish writing proposal before 27/9
| Thu | 2019-09-26
| Fri | 2019-09-27 | Review and approve proposal | MienNTH |  |  | Finish proposal
| Sat | 2019-09-28
| Sun | 2019-09-29
4 | Mon | 2019-09-30 | Prepare survey on English learning habit and need of FU students | PhongVH
| Tue | 2019-10-01 | Attract people to do the survey | AnhPT AnhNN |  | >= 100 people take the survey | >= 100 people take the survey
| Wed | 2019-10-02
| Thu | 2019-10-03
| Fri | 2019-10-04
| Sat | 2019-10-05
| Sun | 2019-10-06 | Summarize information gathered from the survey | TrungDQ
5 | Mon | 2019-10-07 | Decide on detailed content of the handbook | MienNTH |  |  | Have detailed list of items to be included in the handbook
| Tue | 2019-10-08 | Start writing handbook | All |  |  | Finish all handbook content before 12/10
| Wed | 2019-10-09
| Thu | 2019-10-10
| Fri | 2019-10-11
| Sat | 2019-10-12 | Review content Submit to teachers for review | MienNTH AnhPT | Teacher reviews content and give feedback for improvement
| Sun | 2019-10-13
6 | Mon | 2019-10-14 | Format handbook | AnhNN PhongVH |  |  | Finish formatting before 16/10
| Tue | 2019-10-15
| Wed | 2019-10-16 | Submit to teacher for review | MienNTH | Teacher reviews format and give feedback for improvement
| Thu | 2019-10-17
| Fri | 2019-10-18
| Sat | 2019-10-19
| Sun | 2019-10-20
7 | Mon | 2019-10-21 | Write final report | PhongVH AnhPT TrungDQ |  |  | Finish before 25/10
| Tue | 2019-10-22
| Wed | 2019-10-23 | Meet up to track progress | All |  |  | Make sure all finish deadlines on time and clarify any confusion
| Thu | 2019-10-24
| Fri | 2019-10-25
| Sat | 2019-10-26
| Sun | 2019-10-27
8 | Mon | 2019-10-28 | Review and format final report | AnhNN MienNTH |  |  | Finish formatting before 1/11
| Tue | 2019-10-29
| Wed | 2019-10-30 | Send final report to teacher | MienNTH | Teacher reviews and give feedback for improvement
| Thu | 2019-10-31
| Fri | 2019-11-01
| Sat | 2019-11-02
| Sun | 2019-11-03
9 | Mon | 2019-11-04 | Assign presentation tasks for members | MienNTH |  |  | Each member knows what to prepare for presenation. No confusion is left
| Tue | 2019-11-05
| Wed | 2019-11-06 | Make slides for presentation | All | Teacher provides a template for presentation |  | Finish slides for practice before 8/11
| Thu | 2019-11-07
| Fri | 2019-11-08 | Practise speaking for presentation | All |  |  | Each member can present their part fluently
| Sat | 2019-11-09
| Sun | 2019-11-10
10 | Mon | 2019-11-11 | Present about the project in class | All
| Tue | 2019-11-12
| Wed | 2019-11-13 | Submit required documents to teacher | MienNTH
| Thu | 2019-11-14
| Fri | 2019-11-15
| Sat | 2019-11-16
| Sun | 2019-11-17
Formulas:
Date = [Date, row above]+1